{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["作付情報４ 栽培計画"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"作付情報４ 栽培計画","index":0,"n_rows":68,"n_cols":24,"rows_kept":68,"cut":false,"hidden":false,"merged":[]}
["作付グループ","作付ID","作付名","作目","作業開始日","作業終了日","項目分類","項目ID","項目名","集計単位","計画（数量）","計画（単位）","時期","計画開始日","計画終了日","作業のポイント注意点","希釈倍数","使用量/10a（数値）","使用量/10a（単位）","農薬散布回数","収穫前日数","農薬メモ","有効成分名","有効成分散布回数"]
["",214601,"コシヒカリ2021","移植水稲","2021-01-01","2021-12-01","作業項目",1018350,"かん水","10aあたり",null,"時間",null,"2021-01-01","2021-01-31",""]
["",214601,"コシヒカリ2021","移植水稲","2021-01-01","2021-12-01","作業項目",1018358,"耕起","10aあたり",null,"時間",null,"2021-01-21","2021-02-28",""]
["",214601,"コシヒカリ2021","移植水稲","2021-01-01","2021-12-01","作業項目",1018376,"片付け","10aあたり",null,"時間",null,"2021-02-11","2021-02-28",""]
["",214601,"コシヒカリ2021","移植水稲","2021-01-01","2021-12-01","作業項目",1018351,"防除","10aあたり",null,"時間",null,"2021-03-01","2021-03-20",""]
["",214601,"コシヒカリ2021","移植水稲","2021-01-01","2021-12-01","作業項目",1018360,"代かき（荒代）","10aあたり",null,"時間",null,"2021-03-21","2021-04-30",""]
["",214601,"コシヒカリ2021","移植水稲","2021-01-01","2021-12-01","作業項目",1183499,"代かき（本代）","10aあたり",null,"時間",null,"2021-04-01","2021-05-10",""]
["",214601,"コシヒカリ2021","移植水稲","2021-01-01","2021-12-01","作業項目",1183500,"田植え","10aあたり",null,"時間",null,"2021-04-21","2021-05-20",""]
["",214601,"コシヒカリ2021","移植水稲","2021-01-01","2021-12-01","肥料",51886,"硫安","10aあたり",20.0,"kg"]
["",214601,"コシヒカリ2021","移植水稲","2021-01-01","2021-12-01","農薬",193746,"クミアイテクリードCフロアブル","10aあたり",2.0,"L",{"$nulls":4},1.0,null,"mL",1,null,"","イプコナゾール",1]
["",214601,"コシヒカリ2021","移植水稲","2021-01-01","2021-12-01","農薬",193746,"クミアイテクリードCフロアブル","10aあたり",2.0,"L",{"$nulls":4},1.0,null,"mL",1,null,"","水酸化第二銅"]
["",214601,"コシヒカリ2021","移植水稲","2021-01-01","2021-12-01","農薬",194664,"ダントツ粒剤","10aあたり",3.0,"kg",{"$nulls":5},4.0,"kg",3,7,"","クロチアニジン",4]
["",214601,"コシヒカリ2021","移植水稲","2021-01-01","2021-12-01","収量",null,"収量","10aあたり",600.0,"kg"]
["",214601,"コシヒカリ2021","移植水稲","2021-01-01","2021-12-01","生育イベント",68792,"出穂",{"$nulls":4},"2021-07-21","2021-08-20",""]
["",214601,"コシヒカリ2021","移植水稲","2021-01-01","2021-12-01","生育イベント",68793,"発芽",{"$nulls":4},"2021-03-01","2021-04-10",""]
["",216773,"コシヒカリ　2021　育苗","移植水稲","2021-02-01","2021-08-01","農薬",193746,"クミアイテクリードCフロアブル","合計",15.0,"mL",{"$nulls":4},1.0,null,"mL",1,null,"","水酸化第二銅"]
["",216773,"コシヒカリ　2021　育苗","移植水稲","2021-02-01","2021-08-01","農薬",193746,"クミアイテクリードCフロアブル","合計",15.0,"mL",{"$nulls":4},1.0,null,"mL",1,null,"","イプコナゾール",1]
["",217842,"だいこん2021","だいこん","2021-01-01","2022-02-08","作業項目",1018358,"耕起","10aあたり",1.0,"時間",null,"2021-02-01","2021-02-28",""]
["",217842,"だいこん2021","だいこん","2021-01-01","2022-02-08","作業項目",1018350,"かん水","10aあたり",1.0,"時間",null,"2021-03-01","2021-06-20",""]
["",217842,"だいこん2021","だいこん","2021-01-01","2022-02-08","作業項目",1067221,"肥料散布","10aあたり",0.5,"時間",null,"2021-03-01","2021-03-31",""]
["",217842,"だいこん2021","だいこん","2021-01-01","2022-02-08","作業項目",1018357,"播種","10aあたり",0.5,"時間","肥料散布から3日後","2021-03-04","2021-04-03","種子と種子の間隔を15cm以上空ける。"]
["",217842,"だいこん2021","だいこん","2021-01-01","2022-02-08","作業項目",1018351,"防除","10aあたり",0.5,"時間",null,"2021-04-11","2021-05-20",""]
["",217842,"だいこん2021","だいこん","2021-01-01","2022-02-08","作業項目",1018376,"片付け","10aあたり",1.5,"時間",null,"2021-07-01","2021-08-10",""]
["",217842,"だいこん2021","だいこん","2021-01-01","2022-02-08","農薬",193255,"ナブ乳剤","10aあたり",2.0,"L",{"$nulls":4},500.0,200.0,"mL",1,14,"通常の使用基準よりも薄めて使用する。","セトキシジム",1]
["",217842,"だいこん2021","だいこん","2021-01-01","2022-02-08","農薬",194664,"ダントツ粒剤","10aあたり",3.0,"kg",{"$nulls":5},6.0,"kg",1,null,"","クロチアニジン",3]
["",217842,"だいこん2021","だいこん","2021-01-01","2022-02-08","生育イベント",68793,"発芽",{"$nulls":4},"2021-04-21","2021-05-10",""]
["",235625,"こしいぶき2020","移植水稲","2020-01-01","2020-12-31","作業項目",1018350,"かん水","10aあたり",null,"時間",null,"2021-01-01","2021-01-31",""]
["",235625,"こしいぶき2020","移植水稲","2020-01-01","2020-12-31","作業項目",1018358,"耕起","10aあたり",null,"時間",null,"2021-01-21","2021-02-28",""]
["",235625,"こしいぶき2020","移植水稲","2020-01-01","2020-12-31","作業項目",1018376,"片付け","10aあたり",null,"時間",null,"2021-02-11","2021-02-28",""]
["",235625,"こしいぶき2020","移植水稲","2020-01-01","2020-12-31","作業項目",1018351,"防除","10aあたり",null,"時間",null,"2021-03-01","2021-03-20",""]
["",235625,"こしいぶき2020","移植水稲","2020-01-01","2020-12-31","農薬",193746,"クミアイテクリードCフロアブル","10aあたり",2.0,"L",{"$nulls":4},1.0,null,"mL",1,null,"","水酸化第二銅"]
["",235625,"こしいぶき2020","移植水稲","2020-01-01","2020-12-31","農薬",193746,"クミアイテクリードCフロアブル","10aあたり",2.0,"L",{"$nulls":4},1.0,null,"mL",1,null,"","イプコナゾール",1]
["",237313,"コシヒカリ2019","移植水稲","2019-01-01","2019-12-01","作業項目",1018350,"かん水","10aあたり",null,"時間",null,"2021-01-01","2021-01-31",""]
["",237313,"コシヒカリ2019","移植水稲","2019-01-01","2019-12-01","作業項目",1018358,"耕起","10aあたり",null,"時間",null,"2021-01-21","2021-02-28",""]
["",237313,"コシヒカリ2019","移植水稲","2019-01-01","2019-12-01","作業項目",1018376,"片付け","10aあたり",null,"時間",null,"2021-02-11","2021-02-28",""]
["",237313,"コシヒカリ2019","移植水稲","2019-01-01","2019-12-01","作業項目",1018351,"防除","10aあたり",null,"時間",null,"2021-03-01","2021-03-20",""]
["",237313,"コシヒカリ2019","移植水稲","2019-01-01","2019-12-01","農薬",193746,"クミアイテクリードCフロアブル","10aあたり",2.0,"L",{"$nulls":4},1.0,null,"mL",1,null,"","水酸化第二銅"]
["",237313,"コシヒカリ2019","移植水稲","2019-01-01","2019-12-01","農薬",193746,"クミアイテクリードCフロアブル","10aあたり",2.0,"L",{"$nulls":4},1.0,null,"mL",1,null,"","イプコナゾール",1]
["",257199,"ほうれん草","ほうれんそう","2021-05-01","2021-12-01","作業項目",1149364,"畑の準備","10aあたり",8.0,"時間",null,"2021-06-01","2021-06-10",""]
["",257199,"ほうれん草","ほうれんそう","2021-05-01","2021-12-01","肥料",58054,"堆肥","合計",300.0,"kg"]
["",257199,"ほうれん草","ほうれんそう","2021-05-01","2021-12-01","農薬",212447,"除草剤","合計",10.0,"L",{"$nulls":6},"kg",null,null,""]
["",257199,"ほうれん草","ほうれんそう","2021-05-01","2021-12-01","農薬",212448,"殺虫剤","合計",5.0,"L",{"$nulls":6},"kg",null,null,""]
["",257199,"ほうれん草","ほうれんそう","2021-05-01","2021-12-01","資材",24598,"マルチシート","合計",2.0,"本"]
["",257199,"ほうれん草","ほうれんそう","2021-05-01","2021-12-01","資材",24599,"シートアンカー","合計",2.0,"箱"]
["",257199,"ほうれん草","ほうれんそう","2021-05-01","2021-12-01","出荷期間",{"$nulls":6},"2021-08-21","2021-09-30"]
["",273848,"こしいぶき2021","移植水稲","2021-01-01","2021-12-01","作業項目",1018350,"かん水","10aあたり",null,"時間",null,"2021-01-01","2021-01-31",""]
["",273848,"こしいぶき2021","移植水稲","2021-01-01","2021-12-01","作業項目",1018358,"耕起","10aあたり",null,"時間",null,"2021-01-21","2021-02-28",""]
["",273848,"こしいぶき2021","移植水稲","2021-01-01","2021-12-01","作業項目",1018376,"片付け","10aあたり",null,"時間",null,"2021-02-11","2021-02-28",""]
["",273848,"こしいぶき2021","移植水稲","2021-01-01","2021-12-01","作業項目",1018351,"防除","10aあたり",null,"時間",null,"2021-03-01","2021-03-20",""]
["",273848,"こしいぶき2021","移植水稲","2021-01-01","2021-12-01","作業項目",1018360,"代かき（荒代）","10aあたり",null,"時間",null,"2021-03-21","2021-04-30",""]
["",273848,"こしいぶき2021","移植水稲","2021-01-01","2021-12-01","作業項目",1183499,"代かき（本代）","10aあたり",null,"時間",null,"2021-04-01","2021-05-10",""]
["",273848,"こしいぶき2021","移植水稲","2021-01-01","2021-12-01","作業項目",1183500,"田植え","10aあたり",null,"時間",null,"2021-04-21","2021-05-20",""]
["",273848,"こしいぶき2021","移植水稲","2021-01-01","2021-12-01","肥料",51886,"硫安","10aあたり",20.0,"kg"]
["",273848,"こしいぶき2021","移植水稲","2021-01-01","2021-12-01","農薬",193746,"クミアイテクリードCフロアブル","10aあたり",2.0,"L",{"$nulls":4},1.0,null,"mL",1,null,"","水酸化第二銅"]
["",273848,"こしいぶき2021","移植水稲","2021-01-01","2021-12-01","農薬",193746,"クミアイテクリードCフロアブル","10aあたり",2.0,"L",{"$nulls":4},1.0,null,"mL",1,null,"","イプコナゾール",1]
["",273848,"こしいぶき2021","移植水稲","2021-01-01","2021-12-01","農薬",194664,"ダントツ粒剤","10aあたり",3.0,"kg",{"$nulls":5},4.0,"kg",3,7,"","クロチアニジン",4]
["",273848,"こしいぶき2021","移植水稲","2021-01-01","2021-12-01","収量",null,"収量","10aあたり",600.0,"kg"]
["",273848,"こしいぶき2021","移植水稲","2021-01-01","2021-12-01","生育イベント",68792,"出穂",{"$nulls":4},"2021-07-21","2021-08-20",""]
["",273848,"こしいぶき2021","移植水稲","2021-01-01","2021-12-01","生育イベント",68793,"発芽",{"$nulls":4},"2021-03-01","2021-04-10",""]
["",340479,"だいこん2022","だいこん","2022-01-01","2023-02-08","作業項目",1018358,"耕起","10aあたり",1.0,"時間",null,"2022-02-01","2022-02-28",""]
["",340479,"だいこん2022","だいこん","2022-01-01","2023-02-08","作業項目",1018350,"かん水","10aあたり",1.0,"時間",null,"2022-03-01","2022-06-20",""]
["",340479,"だいこん2022","だいこん","2022-01-01","2023-02-08","作業項目",1067221,"肥料散布","10aあたり",0.5,"時間",null,"2022-03-01","2022-03-31",""]
["",340479,"だいこん2022","だいこん","2022-01-01","2023-02-08","作業項目",1018357,"播種","10aあたり",0.5,"時間","肥料散布から3日後","2022-03-04","2022-04-03","種子と種子の間隔を15cm以上空ける。"]
["",340479,"だいこん2022","だいこん","2022-01-01","2023-02-08","作業項目",1018351,"防除","10aあたり",0.5,"時間",null,"2022-04-11","2022-05-20",""]
["",340479,"だいこん2022","だいこん","2022-01-01","2023-02-08","作業項目",1018376,"片付け","10aあたり",1.5,"時間",null,"2022-07-01","2022-08-10",""]
["",340479,"だいこん2022","だいこん","2022-01-01","2023-02-08","農薬",193255,"ナブ乳剤","10aあたり",2.0,"L",{"$nulls":4},500.0,200.0,"mL",1,14,"通常の使用基準よりも薄めて使用する。","セトキシジム",1]
["",340479,"だいこん2022","だいこん","2022-01-01","2023-02-08","農薬",194664,"ダントツ粒剤","10aあたり",3.0,"kg",{"$nulls":5},6.0,"kg",1,null,"","クロチアニジン",3]
["",340479,"だいこん2022","だいこん","2022-01-01","2023-02-08","生育イベント",68793,"発芽",{"$nulls":4},"2022-04-21","2022-05-10",""]